## Project Timeline
THE HERITAGE HOTEL MANILA
PROJECT TIMELINE
PHASE 1
TASKS | RESPONSIBLE PARTY FOR THE DEPENDENCIES | STATUS | START DATE | END DATE | Mandays | REMARKS
PROJECT PLANNING | ITI/Heritage Manila | Completed
Kick Off meeting > ITI Presentation of Project Team and Scope > Setting of Expectation | ITI/Heritage Manila | Completed
Software and Hardware Recommendation | ITI/Heritage Manila | Completed
DATA GATHERING | ITI/Heritage Manila | Completed
Submission of Timekeeping and Payroll Policies | ITI/Heritage Manila | Completed
Development of BFRD (Business and Functional Requirements Documentation) | ITI/Heritage Manila | Completed
Discussion and Finalization of BFRD (Meeting) | ITI/Heritage Manila | Completed
BFRD Sign-off | ITI/Heritage Manila | Completed
PROJECT DESIGN AND DEVELOPMENT FOR INSYS ORBIT AND INSYS PAYROLL | ITI | On-going | 2019-05-20 | 2019-08-30
Project Meetings: Discussion of BFRD | ITI |  | 2019-05-20 | 2019-05-20
System Design and Development | ITI |  | 2019-05-20 | 2019-07-20
Development of Test Cases | ITI |  | 2019-05-20 | 2019-07-20
Functional Testing | ITI |  | 2019-07-22 | 2019-08-22
Quality Assurance Testing | ITI
Documentation of Test Result | ITI
Development and deployment of updates based on Test Result | ITI |  | 2019-08-23 | 2019-08-30
System Release | ITI
INSTALLATION & SET-UP | ITI/Heritage Manila |  | 2019-09-02 | 2019-09-05
Server setup/configuration/installation | ITI / Heritage Manila |  | 2019-09-02 | 2019-09-02
Installation of Fscan | ITI |  | 2019-09-02 | 2019-09-02
Configuration and Set-up of Fscan | ITI |  | 2019-09-02 | 2019-09-02
Installation of Insys | ITI |  | 2019-09-03 | 2019-09-03
Configuration and Set-up of InSys | ITI / Heritage Manila |  | 2019-09-03 | 2019-09-03
> Administrative | ITI / Heritage Manila |  | 2019-09-04 | 2019-09-02
> Company Organization | ITI / Heritage Manila |  | 2019-09-04 | 2019-09-02
> Master Reference Codes | ITI / Heritage Manila |  | 2019-09-04 | 2019-09-02
> Data Migration | ITI / Heritage Manila |  | 2019-09-05 | 2019-09-05
SYSTEM TRAINING | ITI |  | 2019-09-09 | 2019-09-09
Key User's Training | ITI |  | 2019-09-09 | 2019-09-09
USER ACCEPTANCE TESTING | ITI/Heritage Manila |  | 2019-09-10 | 2019-09-20
UAT of Key Users | ITI/Heritage Manila |  | 2019-09-10 | 2019-09-12
Submission of UAT Result | ITI/Heritage Manila |  | 2019-09-13 | 2019-09-13
Development and deployment of updates based from UAT run results | ITI/Heritage Manila |  | 2019-09-16 | 2019-09-17
Regression testing and validation | ITI/Heritage Manila |  | 2019-09-18 | 2019-09-19
UAT Sign-off | ITI/Heritage Manila |  | 2019-09-20 | 2019-09-20
PARALLEL RUN 1 : IONS, PEOPLE, TK, PAYROLL Attendance Cut-off:Sept 23rd - Oct 7th Pay Out: Oct 15th | ITI/Heritage Manila |  | 2019-09-16 | 2019-10-15
USER'S TRAINING | Heritage Manila |  | 2019-09-16 | 2019-09-17
FSCAN | ITI/Heritage Manila
Import logs from biometric devices (FSCAN) | ITI/Heritage Manila
Validate Timekeeping logs | ITI/Heritage Manila
IONS | ITI/Heritage Manila
Validation of Logs | ITI/Heritage Manila
Application and Approval of Attendance: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Validation of Attendance | ITI/Heritage Manila
ORBIT | ITI/Heritage Manila
Uploading of Schedule | ITI/Heritage Manila
Uploading/Updating of Attendance Adjustment: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Process Time & Attendance Processing | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Validation of Attendance Result | ITI/Heritage Manila
Adjustment of Attendance based on validation result: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Posting of Time and Attendance | ITI/Heritage Manila
Generate Timekeeping Reports | ITI/Heritage Manila
PAYROLL | ITI/Heritage Manila
Upload/Encode Recurring Deductions: Loans, etc | ITI/Heritage Manila
Upload/Encode Recurring Income: Allowances, etc | ITI/Heritage Manila
Upload/Encode Payroll Adjustments: Income and Deduction | ITI/Heritage Manila
Process of Payroll | ITI/Heritage Manila
Generate INITIAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Validation of Payroll result | ITI/Heritage Manila
Posting of Payroll | ITI/Heritage Manila
Generate FINAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Generate Bank Export file | ITI/Heritage Manila
Generate Bank Advice (Letter of Instruction) | ITI/Heritage Manila
Consolidation & analysis of findings/discrepancies. | ITI/Heritage Manila
Submission of Parallel Concerns | ITI/Heritage Manila
Development and deployment of updates based from Parallel run results | ITI/Heritage Manila
Regression testing and validation | ITI/Heritage Manila
Parallel Sign-off | ITI/Heritage Manila
PARALLEL RUN 2 : IONS, PEOPLE, TK, PAYROLL Attendance Cut-off: Oct 8th - Oct 22nd Pay Out: Oct 31st | ITI/Heritage Manila |  | 2019-10-16 | 2019-10-31
Import logs from biometric devices (FSCAN) | ITI/Heritage Manila
Validate Timekeeping logs | ITI/Heritage Manila
IONS | ITI/Heritage Manila
Validation of Logs | ITI/Heritage Manila
Application and Approval of Attendance: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Validation of Attendance | ITI/Heritage Manila
ORBIT | ITI/Heritage Manila
Uploading of Schedule | ITI/Heritage Manila
Uploading/Updating of Attendance Adjustment: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Process Time & Attendance Processing | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Validation of Attendance Result | ITI/Heritage Manila
Adjustment of Attendance based on validation result: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Posting of Time and Attendance | ITI/Heritage Manila
Generate Timekeeping Reports | ITI/Heritage Manila
PAYROLL | ITI/Heritage Manila
Upload/Encode Recurring Deductions: Loans, etc | ITI/Heritage Manila
Upload/Encode Recurring Income: Allowances, etc | ITI/Heritage Manila
Upload/Encode Payroll Adjustments: Income and Deduction | ITI/Heritage Manila
Process of Payroll | ITI/Heritage Manila
Generate INITIAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Validation of Payroll result | ITI/Heritage Manila
Posting of Payroll | ITI/Heritage Manila
Generate FINAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Generate Bank Export file | ITI/Heritage Manila
Generate Bank Advice (Letter of Instruction) | ITI/Heritage Manila
Generation of Monthly Government reports | ITI/Heritage Manila
SSS Remittances | ITI/Heritage Manila
PHIC Remittances | ITI/Heritage Manila
HDMF Remittances | ITI/Heritage Manila
Submission of Parallel Concerns | ITI/Heritage Manila
Development and deployment of updates based from Parallel run results | ITI/Heritage Manila
Regression testing and validation | ITI/Heritage Manila
Parallel Sign-off | ITI/Heritage Manila
LIVE RUN 1: IONS, PEOPLE, TK, PAYROLL Attendance Cut-off: Oct 23rd - Nov 7th Pay Out: Nov 15th | ITI/Heritage Manila |  | 2019-11-01 | 2019-11-15
Import logs from biometric devices (FSCAN) | ITI/Heritage Manila
Validate Timekeeping logs | ITI/Heritage Manila
IONS | ITI/Heritage Manila
Validation of Logs | ITI/Heritage Manila
Application and Approval of Attendance: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Validation of Attendance | ITI/Heritage Manila
ORBIT | ITI/Heritage Manila
Uploading of Schedule | ITI/Heritage Manila
Uploading/Updating of Attendance Adjustment: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Process Time & Attendance Processing | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Validation of Attendance Result | ITI/Heritage Manila
Adjustment of Attendance based on validation result: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Posting of Time and Attendance | ITI/Heritage Manila
Generate Timekeeping Reports | ITI/Heritage Manila
PAYROLL | ITI/Heritage Manila
Upload/Encode Recurring Deductions: Loans, etc | ITI/Heritage Manila
Upload/Encode Recurring Income: Allowances, etc | ITI/Heritage Manila
Upload/Encode Payroll Adjustments: Income and Deduction | ITI/Heritage Manila
Process of Payroll | ITI/Heritage Manila
Generate INITIAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Validation of Payroll result | ITI/Heritage Manila
Posting of Payroll | ITI/Heritage Manila
Generate FINAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Generate Bank Export file | ITI/Heritage Manila
Generate Bank Advice (Letter of Instruction) | ITI/Heritage Manila
Consolidation & analysis of findings/discrepancies. | ITI/Heritage Manila
Submission of Parallel Concerns | ITI/Heritage Manila
Development and deployment of updates based from Live run results | ITI/Heritage Manila
Regression testing and validation | ITI/Heritage Manila
Live Run 1 Sign-off | ITI/Heritage Manila
LIVE RUN 2: IONS, PEOPLE, TK, PAYROLL Attendance Cut-off: Nov 8th - Nov 22nd Pay Out: Nov 31st | ITI/Heritage Manila |  | 1931-11-16 | 11/31/2019
Import logs from biometric devices (FSCAN) | ITI/Heritage Manila
Validate Timekeeping logs | ITI/Heritage Manila
IONS | ITI/Heritage Manila
Validation of Logs | ITI/Heritage Manila
Application and Approval of Attendance: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Validation of Attendance | ITI/Heritage Manila
ORBIT | ITI/Heritage Manila
Uploading of Schedule | ITI/Heritage Manila
Uploading/Updating of Attendance Adjustment: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Process Time & Attendance Processing | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Validation of Attendance Result | ITI/Heritage Manila
Adjustment of Attendance based on validation result: Leave, OT, Official Business, Missed Log, Change of Time Schedule | ITI/Heritage Manila
Time and Attendance Process | ITI/Heritage Manila
Posting of Time and Attendance | ITI/Heritage Manila
Generate Timekeeping Reports | ITI/Heritage Manila
PAYROLL | ITI/Heritage Manila
Upload/Encode Recurring Deductions: Loans, etc | ITI/Heritage Manila
Upload/Encode Recurring Income: Allowances, etc | ITI/Heritage Manila
Upload/Encode Payroll Adjustments: Income and Deduction | ITI/Heritage Manila
Process of Payroll | ITI/Heritage Manila
Generate INITIAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Validation of Payroll result | ITI/Heritage Manila
Posting of Payroll | ITI/Heritage Manila
Generate FINAL Payroll Report: Register, Other Income, Other Deduction | ITI/Heritage Manila
Generate Bank Export file | ITI/Heritage Manila
Generate Bank Advice (Letter of Instruction) | ITI/Heritage Manila
Generation of Monthly Government reports | ITI/Heritage Manila
SSS Remittances | ITI/Heritage Manila
PHIC Remittances | ITI/Heritage Manila
HDMF Remittances | ITI/Heritage Manila
Submission of Parallel Concerns | ITI/Heritage Manila
Development and deployment of updates based from Live run results | ITI/Heritage Manila
Regression testing and validation | ITI/Heritage Manila
Live Run 2 Sign-off | ITI/Heritage Manila
PHASE 1: IONS, PEOPLE, ORBIT, PAYROLL
PHASE 2: FINAL PAY, JV, ALPHALIST
Formulas:
START DATE = [START DATE, row below]
END DATE = [END DATE, row below]